## Requirements
Requirements Summary
BR No. | Requirement Title | Priority | Status | Sprint | Assigned Developer | Linked US | Linked AC | Notes
BR-001 | Online Return Request Submission | High | Done | Sprint 1 | Tural | US-001 to US-003 | AC-001 to AC-005
BR-002 | Automated Eligibility Check | High | Done | Sprint 1 | Tural | US-004 | AC-006 to AC-009 | 14-day policy + product condition
BR-003 | Digital Approval Workflow | High | In Progress | Sprint 3 | Tural | US-005 to US-007 | AC-010 to AC-015 | Auto-approve under 100 AZN
BR-004 | Customer Return Status Tracking | Medium | In Progress | Sprint 3 | Rashad | US-008 to US-009 | AC-016 to AC-019 | Email + SMS notifications
BR-005 | Warehouse Pickup Notification | Medium | Not Started | Sprint 4 | Tural | US-010 | AC-020 to AC-022
BR-006 | Refund Processing Integration | High | Not Started | Sprint 4 | Rashad | US-011 to US-013 | AC-023 to AC-028 | Finance team dependency

## Sprint Board
Sprint Board
Sprint | Sprint Goal | Stories | Status | Start Date | End Date | Blockers | Expected Delivery | Actual Delivery | Notes
Sprint 1 | Online return request + eligibility check | US-001 to US-004 | Done | 2026-04-06 | 2026-04-17 | None | 2026-04-17 | 2026-04-17 | On time
Sprint 2 | Database schema + API setup | US-005 (partial) | Done | 2026-04-20 | 2026-05-01 | None | 2026-05-01 | 2026-05-01 | DB design took extra day
Sprint 3 | Approval workflow + status tracking | US-005 to US-009 | In Progress | 2026-05-04 | 2026-05-15 | Notification service delay | 2026-05-15 |  | Waiting for SMS provider
Sprint 4 | Warehouse notification + refund integration | US-010 to US-013 | Not Started | 2026-05-18 | 2026-05-29 |  | 2026-05-29
Sprint 5 | UAT + bug fixes + production release | US-014+ | Not Started | 2026-06-01 | 2026-06-12 |  | 2026-06-12

## Action Items
Action Items
Date | Description | Owner | Deadline | Status | Priority | Related BR/US | Follow-up Date | Notes
2026-04-28 | Update BR-003 approval threshold from 200 to 100 AZN | Zamir | 2026-04-29 | Done | High | BR-003, US-005 | 2026-04-29 | Elnar approved
2026-04-29 | Clarify AC-012 photo size limit with Aysel | Zamir | 2026-04-30 | Done | High | AC-012 | 2026-04-30 | Max 5 MB confirmed
2026-05-01 | Review API documentation from Tural | Zamir | 2026-05-04 | In Progress | High | BR-001 to BR-003 | 2026-05-04
2026-05-02 | Schedule UAT kickoff meeting with stakeholders | Zamir | 2026-05-15 | Not Started | Medium | All |  | Depends on Sprint 3
2026-05-02 | Get SMS provider options from IT department | Ramin | 2026-05-06 | In Progress | High | BR-004 | 2026-05-06 | Sprint 3 blocker

## Decisions Log
Decisions Log
Date | Decision | Requested By | Discussed With | Rationale | Impact | Related BR/US | Status | Notes
2026-04-10 | Mobile app will NOT be built in V1 | Elnar (Sponsor) | Ramin, Tural, Zamir | Budget constraint (80K AZN) and 3-month timeline | Reduced scope, web-only | Scope | Approved | Documented in BRD section 4
2026-04-12 | Auto-approve returns under 100 AZN | Tural (Lead Dev) | Ramin, Zamir | Reduces approval bottleneck, 70% under 100 AZN | Simplified workflow | BR-003 | Approved
2026-04-15 | Photo upload optional for returns | Narmin (Support) | Zamir, Aysel | Customers may not have photos | Max 5 MB, JPG/PNG only | US-001 | Approved | Aysel updated AC-003
2026-04-22 | Notifications via Email + SMS | Zamir | Tural, Ramin | Customers need real-time updates | Added SMS provider dependency | BR-004 | Approved | Sprint 3 blocker
2026-04-28 | Return policy 14 to 30 days (change request) | Elnar (Sponsor) | Ramin, Tural, Zamir | Marketing team feedback | Affects 4 US, 8 AC, +2 dev days | BR-001, BR-002 | Pending | Needs sprint plan update

## Risk Register
Risk Register
Risk ID | Risk Description | Impact | Probability | Risk Score | Mitigation Plan | Owner | Status | Notes
RSK-001 | SMS provider not selected by Sprint 3 start | High | Medium | 6 | Ask Ramin to escalate to IT by April 30 | Ramin | Open | Sprint 3 blocker
RSK-002 | Area manager unavailable for approval (2-3 hr wait) | Medium | High | 6 | Auto-approve under 100 AZN (reduces 70%) | Tural | Mitigated | Decision D-002
RSK-003 | Finance team cannot complete UAT on schedule | High | Low | 3 | Schedule UAT 2 weeks in advance | Zamir | Open
RSK-004 | Scope creep from stakeholder change requests | Medium | High | 6 | Formal change request process | Zamir | Open | Already happened once
RSK-005 | Database performance with large return volumes | Medium | Low | 3 | Tural to run load tests in Sprint 4 | Tural | Open

## Stakeholder Map
Stakeholder Map
Name | Role | Department | Email / Phone | Interest | Influence | Key Concerns | Comm. Frequency | Notes
Elnar Huseynov | Head of Retail / Sponsor | Retail | elnar@kontakt.az | High | High | Budget, timeline, customer satisfaction | Weekly | Approves scope and budget
Ramin Aliyev | Project Manager | PMO | ramin@kontakt.az | High | High | Sprint delivery, resources, risks | Daily | Main contact for schedule
Tural Mammadov | Lead Developer | IT | tural@kontakt.az | Medium | High | Tech feasibility, architecture | Daily | Primary tech decision maker
Rashad Karimov | Backend Developer | IT | rashad@kontakt.az | Medium | Medium | API design, database | Daily (standup) | Working on BR-004
Aysel Ahmadova | QA Tester | IT | aysel@kontakt.az | Medium | Medium | Test coverage, clear AC | Daily (standup) | Reviews all AC
Leyla Hasanova | Store Manager | Retail | leyla@kontakt.az | High | Low | Customer complaints, wait times | Bi-weekly | UAT business user
Narmin Guliyeva | Customer Support Lead | Support | narmin@kontakt.az | High | Medium | Call volume, self-service | Bi-weekly | 40% calls are returns
Samir Abdullayev | Warehouse Supervisor | Logistics | samir@kontakt.az | Medium | Low | Pickup scheduling, storage | Monthly | Needs advance notice
Rasul Novruzov | Finance Officer | Finance | rasul@kontakt.az | Medium | Medium | Refund accuracy | Bi-weekly | Single point of failure

## Meeting Notes
Meeting Notes
Date | Meeting Type | Attendees | Agenda | Discussion | Decisions | Action Items
2026-04-28 | Sprint Planning | Ramin, Tural, Rashad, Aysel, Zamir | Select stories for Sprint 3 | US-005 to US-009 selected. SMS provider concern raised. | Auto-approve under 100 AZN confirmed | Zamir: Review API docs by May 4. Ramin: Get SMS options by May 6.
2026-04-25 | Backlog Refinement | Ramin, Tural, Zamir | Review Sprint 4 stories | US-010 needs more detail. Integration with logistics system. | US-010 needs rewrite | Zamir: Rewrite US-010 by May 1.
2026-04-22 | Change Request Review | Elnar, Ramin, Zamir | 14 to 30 day policy change | Marketing wants 30 days. Impact: 4 US, 8 AC, +2 dev days. | Pending Ramin update | Zamir: Update US/AC. Ramin: Update sprint plan.

## Traceability
Requirements Traceability Matrix
BR No. | BR Title | User Stories | Acceptance Criteria | API Endpoints | Test Cases | Status
BR-001 | Online Return Request | US-001, US-002, US-003 | AC-001 to AC-005 | POST /api/returns GET /api/returns/{id} POST /api/returns/{id}/cancel | TC-001 to TC-008 | Done
BR-002 | Eligibility Check | US-004 | AC-006 to AC-009 | GET /api/returns/eligibility/{productId} | TC-009 to TC-012 | Done
BR-003 | Approval Workflow | US-005, US-006, US-007 | AC-010 to AC-015 | POST /api/approvals PUT /api/approvals/{id} GET /api/approvals/pending | TC-013 to TC-020 | In Progress
BR-004 | Status Tracking | US-008, US-009 | AC-016 to AC-019 | GET /api/returns/{id}/status POST /api/notifications | TC-021 to TC-025 | In Progress
BR-005 | Warehouse Notification | US-010 | AC-020 to AC-022 | POST /api/warehouse/pickup GET /api/warehouse/schedule | TC-026 to TC-028 | Not Started
BR-006 | Refund Processing | US-011, US-012, US-013 | AC-023 to AC-028 | POST /api/refunds GET /api/refunds/{id} PUT /api/refunds/{id} | TC-029 to TC-035 | Not Started